## Slide 1: Radar Odometry
Research Project weekly updates

## Slide 2: Table of Content

## Slide 3: Period Highlight - 4
Implementation of Vx and Vy
Validation of Vx and Vy
Obtain IMU

## Slide 4: Period Highlight - 5
Progress
  Python script with Vx and Vy.
  Read Mti (IMU) sensor.
  mmWave sensor Mount.
Next steps
  Print MTi sensor mount.
  Test sensor fusion recording.
  Validate implementation of Vx and Vy .
  Implement Vx and Vy with IMU values, for rotation.

## Slide 5: Period Highlight – 5 Vx & Vy Components

## Slide 6: Period Highlight – 5 Sensor Fusion

## Slide 7: Period Highlight – 5 Hardware Implementations

## Slide 8: Period Highlight - 6
Progress
  Work and improve recording script for concurrent recording.
  Print IMU sensor mount.
Next steps
  Test in lab.
  No access to lab this period.

## Slide 9: Period Highlight – 7
Progress
  Concurrent sensor logs.
  IMU sensor mount.
Problems
  IMU sensor mount broke.
Next steps
  Incorporate new logs with visualization.
  Incorporate VxVy with IMU data.
    Investigate the role in this before implementation.
    Create a draft.
  Print again the IMU sensor mount.
  Discuss second radar sensor. (?)

## Slide 10: Period Highlight – 7 Sensor Fusion

## Slide 11: Period Highlight – 7 Hardware Implementations

## Slide 12: Period Highlight – 7 Hardware Implementations

## Slide 13: Period Highlight - #

## Slide 14: Period Highlight - #