## Project Planner
Radar Odometry
14.March.2025 - 30.August.2025 |  |  |  |  | Period Highlight: | 4 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Goal | 1 | 24 | 1 | 0 | 0%
Project Proposal | 2 | 3 | 2 | 3 | 50%
Activity Planner | 3 | 2 | 3 | 0 | 75%
Install solidworks | 3 | 1 | 3 | 0 | 50%
Sensor 3d model mount (Draft) | 3 | 1 | 3 | 0 | 0%
Sensor 3d model mount (Design) | 5 | 2 | 5 | 0 | 0%
Basics of ML self study | 1 | 12 | 1 | 0 | 30%
ML Regression | 1 | 8 | 1 | 3 | 25%
Classification | 1 | 8 | 1 | 0 | 0%
Clustering | 1 | 8 | 1 | 1 | 100%
Reinforcement Learning | 1 | 8 | 1 | 1 | 0%
Odometry Papers Material | 1 | 3 | 1 | 4 | 50%
Sensor 3d model mount | 0 | 0 | 0 | 0 | 0%
Sensor 3d model print | 0 | 0 | 0 | 0 | 0%
Plan A | x | x | x | x | x
Implement Odometry using Python | 6 | 6 | 0 | 0 | 0%
Code migration (Py->C++) | 12 | 4 | 0 | 0 | 0%
Occupancy grid w/Bayesian filter | 16 | 2 | 0 | 0 | 0%
Create remote twin of occupancy grid | 18 | 4 | 0 | 0 | 0%
SLAM as ground truth research | 2 | 4 | 3 | 0 | 5%
Wheel speed vs Accel | 4 | 1 | 4 | 0 | 0%
Paper development | 22 | 4 | 0 | 0 | 0%
Plan B | x | x | x | x | x
3 Sensors integration | 4 | 2 | 0 | 0 | 0%
3 Sensors calibration | 6 | 1 | 0 | 0 | 0%
3 Sensors data recolection | 8 | 1 | 0 | 0 | 0%
3 Sensors object detection | 12 | 2 | 0 | 0 | 0%
3 Sensors object detection mapping | 15 | 4 | 0 | 0 | 0%
3 Sensors occupancy grid | 19 | 1 | 0 | 0 | 0%
3 Sensors occupancy grid w/Bayesian filter | 20 | 2 | 0 | 0 | 0%
SLAM as ground truth research | 2 | 4 | 2 | 0 | 5%
Wheel speed vs Accel | 3 | 1 | 0 | 0 | 0%
Paper development | 22 | 4 | 0 | 0 | 0%
Activity 15 | 0 | 0 | 0 | 0 | 0%
Activity 16 | 0 | 0 | 0 | 0 | 0%
Activity 17 | 0 | 0 | 0 | 0 | 0%
Activity 18 | 0 | 0 | 0 | 0 | 0%
Activity 19 | 0 | 0 | 0 | 0 | 0%
Activity 20 | 0 | 0 | 0 | 0 | 0%
Activity 21 | 0 | 0 | 0 | 0 | 0%
Activity 22 | 0 | 0 | 0 | 0 | 0%
Activity 23 | 0 | 0 | 0 | 0 | 0%
Activity 24 | 0 | 0 | 0 | 0 | 0%
Activity 25 | 0 | 0 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%